## TIMELINE
EVENT NAME | [14 empty] | Timeline
Event Details: Project Manager, date, venue
|  |  | Month |  |  |  | Month |  |  |  | Month |  |  |  | Month
TASK | WHO | Wk1 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4 | Wk1 | Wk2 | Wk3 | Wk4
|  | 3-9 | Date
PRE-EVENT
Read review of previous event
Brainstorm & collate ideas for event
Gain funding - sponsorship, grant
Create/update Event Planning Workbook (budget, timeline)
Plan event marketing
Create/update marketing collateral - posters, flyers, banner and advertising
Apply for road closures
Update website, event llistings and create Facebook event
Site visit, measure up space and draft site map
Source performers (signed Letter of Engagement)
Liaise with local police station re: police presence at the event
Liaise with local businesses regarding their involvement and promotion eg flyers
Outline volunteer requirements and source volunteers
Plan event signage
Plan VIP and public parking
Order Council rubbish bins & skip bins, confirm details, update workbook
Book service providers (First Aid & Security), confirm details, update workbook
Order portable toilets, confirm details, update workbook
Food vendors researched, approached, applications processed and permits received
Stall holders researched, approached, applications processed and permits received
Create/update Risk Management Plan
Confirm infrastructure requirements eg food vendors, food court, audience, site office, childrens activities
Finalise performer program
Outline staffing requirements and source event staff
Final event brief sent to stallholders including stall holder info, vehicle access and parking map, site map, entertainment program
Liaise with Visitors Centre regarding Site Office setup and runningsheet
Create/update stakeholder survey
Finalise runningsheet
Permits, road closures & purchase orders complete, printed & filed
Shopping for event equipment & requirements
Prepare event kits & equipment
Print event files, Risk Management Plan and staff clip boards
Charge & pack radios
Pack ute
EVENT
Bump In: - Green room - water, cups, refreshments - Site Office - folder, banners - Banners - CoA, Smokefree - Bin placement - Stallholder placement - Food court area - Performance area - Toilets, first aid station - Childrens activities set up - Stage, lighting and audio - Brief staff, services & volunteers
Event occurs
Bump Out: - Pack up all equipment - bump out all contractors, stall holders etc - Lock all portable toilets - Litter pickup
POST-EVENT
Follow up and process invoices
Post Event Evaluation (Surveys, Thank you letters, Report, Debriefs & Debrief matrix)
Complete Debrief Matrix
Finalise Project Management Systems (Event folder, workbook & working budget)
Sponsorship acquittals/reports

## BUDGET
EVENT NAME
Event Details: Project Manager, date, venue | [5 empty] | Budget
INCOME
SUPPLIER | Income Details - Grant, Sponsorship, Event Revenue | Ref # | FORECAST $ | AMOUNT (excl. GST) | AMOUNT (incl. GST) | COMMENTS
|  |  | 0 | 0 | 0
EXPENSES
SUPPLIER | Expense Details | Ref # | FORECAST $ | COST (excl. GST) | COST (incl. GST) | COMMENTS
SERVICES
First Aid
Security
Electrical Compliance
Event Staff
|  |  | 0 | 0 | 0
INFRASTRUCTURE
Waste - rubbish bins, skip bins
Portable Toilets
Marquees & Furniture - trestles, tables, chairs, umbrellas
Electrical Equipment - generators, lighting towers
Stage, Audio & Lighting
Fencing
Event Themeing
Radios
|  |  | 0 | 0 | 0
ENTERTAINMENT
MC
Headline Act
Support Act
|  |  | 0 | 0 | 0
CHILDRENS ACTIVITIES
Face Painter
Activity #1
Activity #2
|  |  | 0 | 0 | 0
MISCELLANEOUS
Refreshments
Petty Cash
Contingency (3%)
|  |  | 0 | 0 | 0
MARKETING
Collateral Design - poster, flyer, banner, advertisement, program etc
Collateral print
Advertising - media
Advertising - online
Merchandise
|  |  | 0 | 0 | 0
TOTAL |  |  | 0 | 0 | 0

## CONTACTS
EVENT NAME
Event Details: Project Manager, date, venue | [5 empty] | Contacts
ORGANISATION | MAIN/ONSITE | FIRST NAME | SURNAME | PHONE | EMAIL | DETAILS
SPONSORS
SERVICES
First Aid
Security
Electrical Compliance
Event Staff
Radios
INFRASTRUCTURE
Waste - rubbish bins, skip bins
Portable Toilets
Marquees & Furniture - trestles, tables, chairs, umbrellas
Electrical Equipment - generators, lighting towers
Stage, Audio & Lighting
Fencing
Event Themeing
ENTERTAINMENT
MC
Headline Act
Support Act
CHILDRENS ACTIVITIES
Face Painter
Activity #1
Activity #2
STALL HOLDERS
MARKETING
Collateral Design - poster, flyer, banner, advertisement, program etc
Collateral print
Advertising - media
Advertising - online
Merchandise

## RUNNING SHEET
EVENT NAME
Event Details: Project Manager, date, venue |  |  | Runningsheet
Pre-Event Requirements
Day/Time | Task | Staff Name | Notes
Event Schedule
Time | Task | Staff Name | Notes

## BRING LIST
Bring List
ITEM | QTY | LOCATION | AREA DROP OFF
Orange Bollards (for VIP & ACROD car parking) |  | Depot
Star pickets (to secure bins) |  | Event Shed
Examiner Banner |  | Event Shed
Diesel Gerry Can (to be filled at depot) |  | Event Shed
Fire Extinguishers |  | Event Shed
SIGNAGE KIT - Duct tape, cloth tape, danger tape, twine, rope, cable ties, sissors, ground spray paint, measuring tape, staple gun, velcro tape, mallet, stanley knives |  | Event Shed
Directional signage & signage plan |  | Office
GROUNDS KEEPING KIT - Hi Vis Vests, Star picket tops, bin bags, litter collection bags, disposable gloves |  | Event Shed
Hand towels and toilet rolls |  | Properties
Litter pick up tools |  | Event Shed
Orange litter bags |  | Event Shed
Black bin liners |  | Event Shed
Orange flag bunting |  | Event Shed
Tool Kit |  | Event Shed
SITE OFFICE KIT - clipboards, folders, hand wipes, torches, disposable gloves, sharp objects disposal box, lanyards & event staff cards, sunscreen, sissors, pens, tape, blue tak, first aid kit, electrical chords, stanley knife |  | Office
INFORMATION DESK KIT - folder (event program & info, event brief, bus & train timetables, lost child proceedure, incident report form, complaint form, lost property register, relevant CoA forms), large maps & brochures, pens, disposable gloves, sharp object disposal box, tablecloth |  | Office
Water 10l dispensers & paper cups |  | Event Shed
Water (x200) & Sports Drinks (x48) |  | Event Shed
CoA Teardrop Banners (x4 from Comm's ) |  | Comms
CoA Pull up banners |  | Comms
CoA tourism banners & equipment |  | Tourism
CoA stage banner |  | Event Shed
Smokefree Event Teardrop banners |  | Health
Sponsor signage |  | Office
Two-way radios |  | Office
Updated Site Office File - lost child proceedure, Forms: incident report, complaint, declaration of participation, relevant CoA forms Registers: lost property, staff sign in/out, radio sign in/out |  | Office
Dedicated Risk Management File - Risk Management Plan, CoA Crisis Management Plan |  | Office
Event File - Contacts list, full program, staffing lists/scopes of work, logistics matrix, maps etc |  | Office
Parking Clip Boards - VIP list, map, permit
Bunnings list |  | Grocery Shopping List
CoA Signage List

## LOGISTICS MATRIX
EVENT NAME | [16 empty] | Logistics Matrix
Event Details: Project Manager, date, venue | [25 empty] | Amenities |  |  |  | Water & Food | [5 empty] | Signage |  |  |  |  | Crowd Control Fencing
[5 empty] | Marquee |  |  | Van | Own Marquee | Space Only | Power Requirements |  |  | Generators |  | Other |  |  | Tables |  | Other | Main Stage |  |  | Other
Site / Area | Infrastructure Use | Supplier/Responsible | Confirmed | Support/Details | 3x3 | 6x3 | Other |  |  |  | 10amp | 15amp | 32amp | 100KVA | 80KVA | Distribution Boards | Cable Trays | Own Power | Trestle | Round | Chair | Audio | Stage | Lighting | Lighting Towers | Unisex Toilet | Disabled Toilets | Skips Bins | Waste Bins | Ice Tub | Ice | 600ml water | 10l water | 2,000L Water Tank | Snacks | CoA | A Frames | Bali Flags | Smoke Free Banners | Other | Orange Bollard | CCB | Flag Bunting(m) | Mesh Bunting
Stage Area
Food Court
Other Area #1
Other Area #2
Other Area #3
Parking
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## DEBRIEF MATRIX
EVENT NAME
Event Details: Project Manager, date, venue |  |  |  | Debrief Matrix
| Details | Positives | Negatives | Recommendations
General Overview
Time & Date
Venue
Weather
Attendance levels
Overall atmosphere
Bump in
Bump out
Foot-traffic flow
Infrastructure & Services
First aid
Security
Emergency services
Event staff
Electrical compliance
Waste - rubbish bins, skip bins
Portable toilets
Marquees & furniture - trestles, tables, chairs, umbrellas
Electrical equipment - generators, lighting towers
Stage, audio & lighting
Fencing
Event themeing
Event Areas
Overall Site
Floor plan
Lighting
Event signage
Site office
Food Area
Positioning & set up
Furniture - tables, chairs etc
Food vendors
Stage Area
Positioning & set up
Stage Positioning
Audience Positioning
Green room
Headline act
Support act
Buskers
MC
Stall Holders
Positioning & set up
Stall holder guidelines
Stall holder selection
Kids Zones/Activities
Positioning & set up
Activities
Community Engagement
Local entertainers
Local restauranteurs
Local businesses
Local stall holders
Communications and Promotion
Design Concept
Advertising
Editorial
Online
Facebook
Merchandise
Promotional Signage
Feedback